## Sprint 1 Burdown Chart
Burndown Chart
Workshop 1 : Sprint 1
Total Units |  | 66
Due Date |  | 2019-01-18
Date | Day | Jesse | Nick | Evan | Bradley | Zack | Jordan | Jon | Units Input | Actual Units Remaining | Ideal Units Remaining
2019-01-08 | 0 | 1 | [6 empty] | 1 | 65 | 66
2019-01-09 | 1 |  | 1 | 3 |  |  |  |  | 4 | 61 | 59.4
2019-01-10 | 2 | [7 empty] | 0 | 61 | 52.8
2019-01-11 | 3 | [7 empty] | 0 | 61 | 46.2
2019-01-12 | 4 | [7 empty] | 0 | 61 | 39.6
2019-01-13 | 5 | [7 empty] | 0 | 61 | 33
2019-01-14 | 6 | [7 empty] | 0 | 61 | 26.4
2019-01-15 | 7 | [7 empty] | 0 | 61 | 19.8
2019-01-16 | 8 | [7 empty] | 0 | 61 | 13.2
2019-01-17 | 9 | [7 empty] | 0 | 61 | 6.6
2019-01-18 | 10 | [7 empty] | 0 | 61 | 0

## Sprint 1 Tasks
Tasks and Assignments
Workshop 1 : Sprint 1
Tasks | Task Description | Current Status | Priority | Estimated Cost | Actual Cost | Assigned to | Assigned to2 | Assigned to3 | Assigned to4
Game Analytics | Add analytics at every step to track player behavior | planned | 2 | 2 |  | Bradley | Jesse | Jon | Nick
Game on Android | Installing apk build of game to test on android device | planned | 2 | 1 |  | Bradley | Jesse | Nick
UI/UX Implementation | Implementing designed UI into game build | in progress | 1 | 8 |  | Nick
Character Model | Designing and creating character 3d model | planned | 2 | 6 |  | Zach
Create Crate Iterations | Creating crates for each powerup that can be instantiated | planned | 2 | 5 |  | Jordan
Mineshaft Created | Create mineshaft components and implement into Unity as prefabs to be looped | planned | 1 | 11 |  | Jordan
Demo Sound conecpts | Creating demo sounds to test with build of game to see what fits | planned | 3 | 1 |  | Evan
Game Build Recreation | Recreating the game build form sctach in Unity 2018.3.0f2 to move away from prototype code and contstruction | planned | 1 | 16 |  | Jesse | Nick
Create Sound Direction | Making demo sounds to help create sound scapes | in progress | 2 | 8 |  | Jon
Jump Sound | Creating sound for when player jumps | in progress | 2 | 2 |  | Evan
UI Sounds | Sounds to be implemented for interaction with UI | in progress | 2 | 2 |  | Evan
Block Drill Sound | Sounds for when the player breaks blocks with drill | in progress | 2 | 2 |  | Evan
Coin Sound | Sound for when player picks up coins | completed | 2 | 1 | 1 | Evan
Fix gitHub repository | Get github repository corrected so everyone can access and get unity package loaded | completed | 1 | 1 | 1 | Jesse

## Sprint 2 Tasks
Tasks and Assignments
Workshop 1 : Sprint 2
Tasks | Task Description | Current Status | Priority | Estimated Cost | Actual Cost | Assigned to | Assigned to2 | Assigned to3 | Assigned to4
Falling Particles | Create and iterate on particles that could be falling in a mineshaft | planned | 2 | 4
Playable Demo | Having a playable demo that can be playtested on android devices | planned | 1 | 6
Stackable objects | Create and iterate on objects that could be falling in a mineshaft | planned | 1 | 4
UI/UX Implementation | Implementing designed UI into game build and making any changes after playtesting | planned | 1 | 6
Lava Material Created | Create lava material that fits art design | planned | 2 | 4
FMOD Implementation | Implementing FMOD into Unity to create haptic feedback music | planned | 2 | 4
Character Model | Designing and creating character 3d model | planned | 1 | 8

## dropdown lists (hidden)
planned | 1 | Bradley
in progress | 2 | Evan
testing | 3 | Jesse
completed | 4 | Jon
| 5 | Jordan
Nick
Zach